## Slide 1: Integrated Financial Management Information System (IFMIS) - ESWATINI

## Slide 2: AGENDA
Project Overview
Team Collaboration
Stakeholder willingness
Lesson Learnt
Forecasted Risks
Upcoming Tasks and Recommendation

## Slide 3: PROJECT OVERVIEW
Implementation of IFMIS in ESWATINI to manage the Public Finance Management (PFM)
18 Modules to be implemented
Within 4 years, 2 years for implementation and 2 for support
Implementers are RCI (Contractor), QT and MINECOFIN as technical team.

## Slide 4: TEAM COLLABORATION
RCI initiated team synergy on both side, the client and the implementor
Team were splited in 3 categories: Project Management, Business Analysts and Software Technical Developers.
Regural standup meetings in the weekend, to discuss what have been achieved in the past week and plan for the upcoming week
For urgent communication we used Whatsupp Group
We collaborated as Team Rwanda.
We rented the same compound

## Slide 5: STAKEHOLDER WILLINGNESS
Warm welcome to the team
Provision of dedicated transport for our team.
Provided experts from various department of all involved Ministries during the requirement analysis and validation
Respected our schedules during the analysis phases
Positive reaction to requested changes on the specific process
Demostrated willingness to learn from our experience.
Collaboration flexibility on the side of client

## Slide 6: LESSON LEARNT
Domain experts from MINECOFIN
Using standardized methodologies of project implementation and documentation (Ex: Agile, IEEE Documentation standard). Additionally, creating the common template for documentation.
Client has structured processes that make it easier for us to implement IFMIS
Well prepared SRS, with cohesion, consiceness and consistency.

## Slide 7: FORECASTED RISKS
Insuficiency of team members on both sides
Uncertainty in interfacing with external systems that are still under development.
Tight schedule to implement at least COA, Budget and Planning modules before the end of July.
Lack of prerequisites on the side of the client.
Ex:
- Lack of PKI infrastructure
- Approval of the COA by the cabinet
- Lack of Disaster recovery
* Gap in the domain expertise on our side.

## Slide 8: UPCOMING TASKS AND RECOMMENDATION
Development has to be started now on the aforementioned 3 modules
Availability of experts is now
Initiating collaboration framework with the team from MINECOFIN and RCI.
Planning for a dedicated team that will be in ESWATINI in July.
Fast learning in all areas of project implementation. (Business and Technologies).

## Slide 9: THANK YOU!