## Phase I
2024/2025 (May 2024 to March 2025)
Module | Delivery Schedule
General ERP, interface, and reporting Requirements | May, Jun
Chart of Accounts | May, Jun
Planning and Budgeting | May, Jun, Jul, Aug
Debtor Management | Aug, Sep
Vendor Management | Aug, Sep
Accounting | Aug, Sep, Oct, Nov
Revenue Collection (Non-tax receipts) | Sep, Oct, Nov
Procurement | Dec, Jan, Feb
Travel Management | Nov, Dec, Jan
Cash Management | Nov, Dec, Jan
Bank Reconciliation | Sep, Oct, Nov, Dec
Staff Establishment and Payroll Management | Sep, Oct, Nov, Dec, Jan, Feb, Mar